## Slide 1: Dizzy (HL7800)
Project Development Plan
R01.05

## Slide 2: Template Information
Note: The present document is managed in the corporate EDM tool, with the appropriate version control and approval workflow
Document #: | 4124002
Legacy #: | 
Revision: | 01.12
Document Type: | Template
Customer Name : | N/A
Author: | SEPG
Author Document Creation Site: | ILM
Document Location: | FileHold
Notes: Do not update this page, this is for the template itself!

## Slide 3: Template Change History
Revision | Date | Change History | Author
01.00 | 2012/12/03 | Creation | T. Barataud
01.01 | 2012/12/14 | Update after presentation during workshop | P-Y Klein
01.02 | 2013/01/18 | Update of QA plan. Upload in FileHold 4124003 | P-Y Klein
01.03 | 2013/04/17 | Update of QA Plan and Suppliers part | P-Y Klein
01.04 | 2013/06/26 | ACT00181: Give more details about Configuration Management (Source code and audit) | P-Y Klein
01.05 | 2013/07/10 | ACT00191: update of supplier selection chapter | SEPG
01.06 | 2013/11/18 | Use of new corporate template ACT00284: Clarification on the mandatory aspect to have MRD reference on P44 Modification of list of reference documents on P44 | SEPG
01.07 | 2014/01/03 | ACT00242: remove cert. Lab from suppliers eligible to SAM ACT00236: add comment about project meeting frequency and attendees ACT00300: | SEPG
Notes: Do not update this page, this is for the template itself!

## Slide 4: Template Change History
Revision | Date | Change History | Author
01.08 | 2015/02/02 | Update of budget page (ACT00318) and configuration management page (ACT00430). EST file is added to the list of project records. Add the list of people mandatory for gate decisions (ACT00517). Include LL as a milestone in the timeline (ACT00525) | P-Y Klein
01.09 | 2015/02/18 | Update Project Management Deliverables | P-Y Klein
01.10 | 2015/11/03 | Add a topic about certification strategy in the dev approach (ACT00683) and move to latest SWI template | P-Y Klein
01.11 | 2016/07/07 | EPG-406: add a section about product maintenance after the project and replace any reference to SBM with Jira Add ERD as project mandatory record | P-Y Klein
01.12 | 2017/04/25 | EPG-511: Replace Core Team process (obsolete) with PSLT process on References slide and remove Estimation template. Add Product checklist in References and on QA plan slide | P-Y Klein
Notes: Do not update this page, this is for the template itself!

## Slide 5: Document Information
Document #: | 41110746
Legacy #: | 
Revision: | xx.yy
Document Type: | Project Development Plan
Customer Name : | N/A
Author: | Vincent Desortiaux
Author Document Creation Site: | ILM
Document Location: | FileHold
Note: The present document is managed in the corporate EDM tool, with the appropriate version control and approval workflow
Notes: Update this page with the FH ID and other relevant information.

## Slide 6: Change History
Revision | Date | Change History | Author
R01.00 | 2017/07/04 | Creation | Vincent Desortiaux Alban Roche
R01.01 | 2017/07/05 | Slide 20 -> L2 Jira Project update Slide 37/40 -> Organization/Development Approach update. Risk update | Vincent Desortiaux Alban Roche
R01.02 | 2017/07/26 | Major update following project scope change (MRD v2.x) | Vincent Desortiaux
R01.03 | 2017/07/27 | Slide 23: add TMA & Infosys contact names Slide 24: add SSM names Slide 25: replace Alban with Thomas for SW gate preparation Silde 54: add CAPEX note Slide 26: add PQE in project meeting Slide 56/57: risk update Slide 61: add reference to #41111256 Slide 63: add names for each checklist | Vincent Desortiaux
R01.04 | 2017/07/27 | Slide 64: Product Checklist managed by the PQE | Vincent Desortiaux
R01.05 | 2017/07/27 | Slide 25: remove Syst Eng representative | Vincent Desortiaux
Notes: Each time a new version of this document is done, update this table accordingly.

## Slide 7: Full Table of Content - 1
Scope
  Overview
  Make or Buy
  Suppliers
  Project Data
  Project Organization
  Skills & Trainings
  Deliverables
  Maintenance
Key Features
  Hardware Product
  Host SW and Firmware
  Development Approach
Constraints & Dependencies

## Slide 8: Full Table of Content - 2
Schedule & Milestones
  Schedule
  Milestones
Budget
  Product Cost Estimate
  Project Budget
Risks
Monitoring and Control
Configuration Management
Quality Assurance
References
Terms and Acronyms

## Slide 9: Table of Content
Scope
Key Features
Constraints
Schedule & Milestones
Budget
Risks
Monitoring and Control
Configuration Management
Quality Assurance
References
Terms and Acronyms

## Slide 10: Scope - Overview
Dizzy project encompasses phase 1 of HL78 program (as per MRD scope phasing)
HL7800 module is:
  based on Altair 1250 & Skyworks SKY68001
  Cat-M1 & Cat-NB1 3GPP Rel.13
  Power Class 3 (23dBm)
  targeting all carriers with 1 PCA (target)
HL7800 module is compliant with CF3 V2 (Medium size 15x18mm²)
Sierra AT commands are developed on top of Legato RTOS
Lead customers: Itron, L&G, Telular, Resmed

## Slide 11: Scope - Overview
Not in the scope of Dizzy
  HL7802 (4G+2G)
  SW features phase 2 (Secure boot, GNSS, full USB, full AV, Voice)
  Soft SIM / iUICC / in-house personnalisation
  Snap-in socket 15x18 (current MP plan is Q4/2018)

## Slide 12: Scope – Dizzy project versus HL78 program partition
 | HL7800 (Phase 1) = Dizzy | HL7800 (Phase 2) | HL7802 (Phase 3) | HL7800/02 (Phase 4)
Modem | Cat-M1 (EC mode A) Cat-NB1 | RAT switching w/o reset EC Mode B (TBC) | 2G data 2G voice | VoLTE
Connectivity / FW upgrade | FOTA-ready Local upgrade | AV-ready SmartSIM / eUICC ready (TBC) |  | 
Security | Secure socket (TCP/UDP) | Secure socket (HTTPS) Secure boot |  | 
IP | PPP E2E (ATD*99) TCP/UDP/SSL IPv4/IPv6 |  |  | 
GNSS |  | GNSS |  | A-GNSS (Server based)
Serial link | UART 4/ 8-wires | USB FS (w/ ethernet classes) |  | 
AT commands | As per FH#41111103 (WIMEI, CMUX, NVBACKUP,TX/RXPOWER, KSLEEP, CLAC, CPOF, KSREP, Fast Shutdown, KBND,KCELL, GPIO, ADC, CALA, KSRAT, ..) | As per FH#41111103 |  | As per FH#41111103
Regulatories & industry | FCC, IC, CE, JRF/JPA, RCM PTCRB/GCF |  |  | 
Carrier approval | Verizon, AT&T Telstra, T-Mobile, Rogers, Vodafone | TBD | TBD | TBD

## Slide 13: Scope – MRD v2.05 open items (key items)
Req ID | Requirement | Status
01.24/ 25/26 | Automatic Cat-M1/NB1 switching without reset/reboot (+KSRAT), search & selection according to policy set | Pure Altair feature. Automatic RAT switching not confirmed for phase 1. Altair to provide a plan for this feature.
12.02 | CBOM lower than 5$ | FEM change from 20dBm Altair to 23dBm Skyworks is impacting cost by ~50c$ (PA/GPS LNA/RF coupler)
01.43 | DoNAS support | Current Altair delivery mid 2018. Pull-in requested (SoW) Vodafone feature set requirements under clarification
04.68 | Module shall provide protection against over-heating | Pending feasibility & schedule from Altair (SoW)

## Slide 14: Scope - Project Data - 1
Project Code (for Timesheet and Purchase requests): AP16007
Project Name: Dizzy
Clarity: AP16007 Dizzy
JDE Edwards: Dizzy.AP16007
Num Type (PID) : T3
Notes: The information displayed here shall also be available on the « Project Data » spreadsheet of the dashboard, in the section Project repository mainly.
It is advised to put the name of the product together with the project name in Clarity: Centaurus-HL8518